## Project 3
Requirement ID | Description | Story Points | Priority | Sprint Number | Assignee
1 | Set up the Python/Pygame application with a main loop that processes user input, updates game state, and renders the current screen. | 2 | 1 | 1 | Tyler
2 | Implement navigation between the menu, instructions, and active minigame screens. | 1 | 2 | 1 | Tyler
3 | Create a main menu that allows players to select single-player mode or online 1v1 multiplayer mode. | 2 | 3 | 1 | Joshua
4 | Display relevant game information, including the current section, difficulty, remaining lives, and player information. | 1 | 4 | 1 | Trey
5 | Start the selected minigame and initialize its game state. | 1 | 5 | 1 | Trey
6 | Display the selected minigame's instructions and provide a countdown before accepting gameplay input. | 1 | 6 | 1 | John
7 | Allow players to select rock, paper, or scissors and determine the round outcome, including ties. | 1 | 7 | 1 | John
8 | Determine the round winner by comparing player completion times when at least one player finishes. | 1 | 8 | 1 | John
9 | Compare objective-specific progress when neither player finishes before the time limit expires. | 1 | 9 | 1 | Nickan
10 | Detect and handle ties when players achieve equivalent results. | 1 | 10 | 1 | Nickan
11 | Display a round-results screen showing the winner, relevant scores, and updated lives before the next section begins. | 1 | 11 | 1 | Jack
12 | Advance to the next section after the current round finishes and its results have been processed. | 1 | 12 | 1 | Lena
13 | Randomly select a minigame for each section from the available games. | 1 | 13 | 1 | Trey
14 | Implement single-player mode so a player can play through randomly selected minigames without connecting to another player. | 2 | 14 | 1 | Lena
15 | Track each player's remaining lives throughout the session and display the updated total after each round. | 2 | 15 | 1 | Joshua
16 | Deduct a life when a player loses a round. | 1 | 16 | 1 | Jack
17 | Detect when a player runs out of lives, end the match, and declare the overall winner. | 1 | 17 | 1 | Jack
18 | Increase the game's difficulty after each completed section. | 1 | 18
19 | Apply appropriate difficulty adjustments to individual minigames, such as increased speed, longer sequences, or more complex mazes. | 1 | 19
20 | Allow a player to create an online multiplayer session. | 1 | 20
21 | Generate and display a session identifier that another player can use to join the multiplayer session. | 1 | 21
22 | Allow a second player to join an existing multiplayer session using its session identifier. | 2 | 22
23 | Synchronize round starts so both players begin each minigame under the same conditions. | 1 | 23
24 | Synchronize round time limits between multiplayer clients. | 1 | 24
25 | Transmit player inputs between multiplayer clients as needed for gameplay. | 1 | 25
26 | Transmit relevant gameplay events between multiplayer clients. | 1 | 26
27 | Synchronize relevant gameplay-state updates between multiplayer clients. | 1 | 27
28 | Transmit round results between multiplayer clients. | 1 | 28
29 | Validate incoming network messages and handle invalid or unexpected messages without crashing. | 1 | 29
30 | Detect multiplayer disconnections and provide appropriate handling so the application does not permanently freeze or crash. | 1 | 30
31 | Display a reaction cue after a randomized delay using a visual indicator or reaction bar. | 1 | 31
32 | Record each player's valid response time after the reaction cue and report the result for multiplayer comparison. | 2 | 32
33 | Generate a valid maze layout containing walls, traversable paths, portals, and a destination. | 1 | 33
34 | Display the generated maze and its relevant gameplay elements. | 1 | 34
35 | Allow players to navigate the maze using directional input while preventing movement through walls. | 2 | 35
36 | Implement portal transportation and detect when a player reaches the destination, reporting completion or progress for winner determination. | 2 | 36
37 | Generate a sequence of button or color prompts for the Simon Says memory game. | 1 | 37
38 | Display the Simon Says sequence and increase its length as the difficulty rises. | 1 | 38
39 | Accept the player's repeated sequence, detect incorrect inputs, and report whether the player completed the sequence successfully. | 2 | 39
40 | Display timed directional or button instructions for the DDR game and evaluate player inputs based on correctness and timing accuracy. | 2 | 40
41 | Generate a Minesweeper board and place mines while ensuring the initial clicked cell and its neighbors are safe. | 1 | 41
42 | Calculate and display the number of adjacent mines for each relevant Minesweeper cell. | 1 | 42
43 | Allow players to reveal safe Minesweeper cells, including automatically revealing connected safe areas when appropriate. | 1 | 43
44 | Allow players to place and remove flags on suspected Minesweeper mines. | 1 | 44
45 | Detect Minesweeper mine hits and successful completion, then report each player's completion status or progress for winner determination. | 2 | 45
46 | Allow the player to trace a cutting line across the pizza using mouse input. | 1 | 46
47 | Calculate pizza-cutting accuracy based on deviation from the target cutting line. | 2 | 47
48 | Display pizza-cutting accuracy and compare multiplayer results to determine the round winner. | 1 | 48

## Reference Stories
Reference Story Number | Pool | Story Source | Story Summary
1 | 1 | General UI task | Change the color of an existing UI element while preserving its current functionality and layout.
2 | 1 | General UI task | Adjust the font size of existing text to improve readability without changing the surrounding interface.
3 | 1 | General UI task | Move an existing UI element to a different position while preserving its appearance and functionality.
4 | 2 | General coding task | Add comments to a medium-sized section of existing code, such as a small class or large function, to explain its purpose and important logic.
5 | 2 | General UI task | Create a small selection-screen-type UI interface that accepts user input and provides a basic way to interact with the application.
6 | 2 | Minesweeper Project 1 | Define the basic structure of a class, including its constructor or initialization function, attributes, and any necessary function declarations.
7 | 3 | Minesweeper Project 1 | Create a helper function similar to checksquare from the first Minesweeper project that performs a specific task and can be reused by other parts of the program.
8 | 3 | Minesweeper Project 1 | Implement a breadth-first search (BFS)-type function similar to OpenRec from the first Minesweeper project to traverse connected cells and handle their processing.
9 | 3 | Minesweeper Project 1 | Integrate the frontend and backend for the first Minesweeper project by implementing API communication, passing requests and responses, and correctly referencing variables between components.
10 | 5 | Minesweeper Project 1 | Implement the complete Minesweeper user interface, including all necessary UI elements for displaying the board, interacting with cells, and showing game information and controls.
11 | 5 | General game development / Minesweeper | Implement an animation of a bomb exploding, including the necessary visual frames, timing, and integration with the game so the animation plays at the appropriate time.
12 | 5 | General game development / Minesweeper | Create four to five custom sprites by hand, including designing their appearances and preparing them for use in the application's visual interface.
13 | 8 | Minesweeper Project 1 | Complete the first Minesweeper project, including its frontend, backend, API communication, mine placement, cell uncovering, flagging, and core game logic.
14 | 8 | EECS 348 | Implement a simple Node.js file server similar to the EECS 348 assignment that handles incoming requests and serves requested files to clients.
15 | 8 | EECS 468 | Implement the Haskell reverse Polish notation calculator from EECS 468, including parsing input expressions, evaluating operations using a stack, and returning the calculated results.
16 | 13 | EECS 678 | Implement a buddy memory allocator similar to the EECS 678 assignment, including memory allocation and deallocation, splitting and merging memory blocks, and managing free memory.
17 | 13 | Machine learning class project | Develop a machine-learning model using a provided dataset to predict patient outcomes based on diagnosis, including preparing the data, training the model, and evaluating its predictions.
18 | 13 | Robotics class project | Program a physical robot to use its sensors to map a maze and then determine and execute a path through the maze, integrating sensor input, navigation, and movement.
19 | 21 | EECS 678 | Develop Quash or a simplified Linux shell from scratch, including parsing commands, executing programs, handling arguments, and supporting essential shell functionality.
20 | 21 | EECS 348 | Implement the EECS 348 calculator in C++, including its calculation functionality, input handling, error handling, and documentation explaining its design and usage.
21 | 21 | Machine learning class project | Develop a language-guessing application that uses AI integration to identify the language of provided text, including building the application itself and connecting it to the AI functionality.